## Verification Matrix
H02 — Initial Verification Matrix
Project | RudraEdge T1 Testing
System Under Verification | Telemetry Validation & Processing System (TVPS)
Environment | Local / Offline Python Environment
Status | Executed — 15/15 PASS
Req ID | Test Case | Method | Expected Result | Evidence | Status
REQ-001 | TC-001 Valid telemetry acceptance | UT / IT / DEMO | Valid telemetry packet is parsed, validated and accepted | pytest + demo | PASS
REQ-002 | TC-002 Missing mandatory field | UT / FT / DEMO | Packet is rejected and missing field is reported | pytest + demo | PASS
REQ-003 | TC-003 Invalid data type | UT / FT / DEMO | Wrong data type is rejected with clear error information | pytest + demo | PASS
REQ-004 | TC-004 Range and boundary validation | UT / FT / DEMO | Valid boundaries are accepted and out-of-range values are rejected | pytest + demo | PASS
REQ-005 | TC-005 Sequence validation | UT / FT / DEMO | Positive sequence accepted; out-of-order packet is detected and reported | pytest + demo | PASS
REQ-006 | TC-006 Malformed JSON | FT / DEMO | Malformed/truncated JSON is rejected with parsing error | pytest + demo | PASS
REQ-007 | TC-007 Normalised processing result | UT / IT | Valid telemetry produces the required normalized result | pytest | PASS
REQ-008 | TC-008 Structured error handling | FT | Errors are observable and are not silently swallowed | pytest | PASS
REQ-009 | TC-009 Batch processing | IT / DEMO | Batch counters and individual packet results are correct | pytest + demo | PASS
REQ-010 | TC-010 Deterministic processing | UT / IT | Same input produces the same result | pytest | PASS
REQ-011 | TC-011 Local/offline operation | RT / Review | System operates without network, cloud or external runtime dependency | pytest + source review | PASS
REQ-012 | TC-012 Public API verification | UT / RT | Required public functions can be imported and tested independently | pytest | PASS
REQ-013 | TC-013 Complete regression suite | RT | Complete pytest suite executes successfully | pytest -v | PASS
REQ-014 | TC-014 Demo verification | IT / DEMO | run_demo.py executes all reference scenarios successfully | demo output | PASS
REQ-015 | TC-015 Reproducible failure reporting | UT / FT | Failure identifies input condition, function, error type and message | pytest | PASS

## Summary
H02 Verification Summary
Total Requirements | 15
PASS | 15
FAIL | 0
BLOCKED | 0
NOT TESTED | 0
Defects | 0
Pytest Result | 166 passed, exit 0
Demo Result | 8/8 scenarios passed, exit 0